## Iter2
Iteration 2
# | Function/Screen | Feature | Function/Screen Details | In Charge | Status | Notes
1 | Manage Recipes | Admin | This is a pop-up screen which allows the Admin to manage the Recipes Information | HaGTHE153279 | Doing
2 | Manage Customers | Staff | This is a pop-up screen which allows the Admin to manage the Customer Information | HaGTHE153279 | Doing
3 | Manage Orders | Staff/Admin | This is a pop-up screen which allows the Admin to manage the order | HaGTHE153279 | Doing
4 | Java Script for Search, Filter, Pagination | Admin | JavaScript for CRUD | NghiaHTHE153608 | Doing
5 | Find and Add data to Database | Public | Add data to database | Anhdnhhe150204 | Doing
6 | Recipe | Public | Show the recipes of the food | NghiaHTHE153608 | Doing
7 | Ingredient | Public | Show the ingredient of the foods | NghiaHTHE153608 | Doing
8 | Error paging | Public | Show when occur error | Minhtahe153458 | Doing
9 | Forget Password | Public | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. | QuocTHHE150051 | Doing
10 | Edit Profile | Public | This screen allow to edit profile | Anhdnhhe150204 | Doing

## Iter3
Iteration 3
# | Function/Screen | Feature | Function/Screen Details | In Charge | Status | Notes
1 | Recipe Detail | Public | When user click a recipe, user will be transfer to the Detail page of that recipe with its information | NghiaHTHE153608 | Doing
2 | Ingredient Detail | Public | When user click a ingredient, user will be transfer to the Detail page of that ingredient with its information | NghiaHTHE153608 | Doing
3 | Homepage | Public | When User enter the page, the system will get data of some Recipe/Ingredient and display it to the User. The user then can click a Recipe/Ingredient to see the details of it or click View More see more Recipe/Ingredient | NghiaHTHE153608 | Doing
4 | Manage Ingerdient | Admin/Staff | This is a pop-up screen which allows the Admin to manage the Ingredient | HaGTHE153279 | Doing
5 | Manage Category | Admin/Staff | This is a pop-up screen which allows the Admin to manage the Category | HaGTHE153279 | Doing
5 | Post Recipes | Public | Post Recipe for User | QuocTHHE150051 | Doing
6 | View Liked recipes | Public | Show the Recipes that User has posted | QuocTHHE150051 | Doing
7 | View Share | Public | Create button to allow users share their favourite recipes | Minhtahe153458 | Doing
8 | ChangePassWord | Public | This Allow user to change their password | Anhdnhhe150204 | Doing

## Iter4
Iteration 4
# | Function/Screen | Feature | Function/Screen Details | In Charge | Status | Notes
1 | Cart Detail | User | When user click Cart, user will be transfer to the Cart page with User's Cart Info | NghiaHTHE153608 | Doing
2 | Button "Add to Cart" | User | When user click "Add to Cart" in Recipe Detail and Ingredient Detail, the Ingredient of that Recipe will be added to Cart | NghiaHTHE153608 | Doing
3 | Button "Buy Now" | User | When user click "Buy Now" in Recipe Detail, redirect User to Cart with the Ingredient of that Recipe | NghiaHTHE153608 | Doing
4 | Order Detail for Admin | Admin/Staff | This is a pop-up screen which allows the Admin to manage the Order Detail | HaGTHE153279 | Doing
5 | Recipe_Ingredient Link | Admin/Staff | This is a screen which links Recipe with Ingredient | HaGTHE153279 | Doing
6 | Contact page | Public | Show contact number, mail, and QR to contact for help | Anhdnhhe150204 | Doing
6 | Favourite list | Public | Add a recipe to favourite list / Remove a recipe from favourite list | QuocTHHE150051 | Doing
7 | User order hIstory | Public | Show orders history of logged in user | QuocTHHE150051 | Doing
9 | Recipes Comment | Public | This allows user to comment on social recipes that they prefer | Minhtahe153458 | Doing

## Tasks
Project Tasks
Iteration | Output | Task | In-charge | Deadline | Status | Notes
Iter1 | Vertical Prototype | Code/Intergrate/Test User Profile | Anhdnhhe150204 |  | Done
Iter1 | Design Overview | User Profile | Anhdnhhe150204 |  | Done
Iter1 | SRS Overview | Create new Figure for Introduction, write Screen Details | HaGTHE153279 |  | Done
Iter1 | Vertical Prototype | Code/Intergrate/Test User Dashboard | HaGTHE153279 |  | Done
Iter1 | Design Overview | Overview | HaGTHE153279 |  | Done
Iter1 | Design Overview | View list user, edit Account, add Account | HaGTHE153279 |  | Done
Iter1 | Iteration 1 Plan | Create plan for iteration 1 | HaGTHE153279 |  | Done
Iter1 | SRS Overview | Write user authorization, order the roles of Screens | MinhTAHE153458 |  | Done
Iter1 | Vertical Prototype | Code/Intergrate/Test User Dashboard | MinhTAHE153458 |  | Done
Iter1 | SRS Overview | Draw Screen flow | NghiaHTHE153608 |  | Done
Iter1 | Vertical Prototype | Code/Intergrate/Test HomePage | NghiaHTHE153608 |  | Done
Iter1 | Vertical Prototype | Add cookies to every page | NghiaHTHE153608 |  | Done
Iter1 | Vertical Prototype | Code/Intergrate/Test Admin Dashboard | NghiaHTHE153608 |  | Done
Iter1 | SRS Overview | Write Introduction about FoodWhale System, list all Non- Screen Functions and their descriptions | QuocTHHE150051 |  | Done
Iter1 | SRS Overview | Write Functional Requirements for vertical prototype | QuocTHHE150051 |  | Done
Iter1 | Vertical Prototype | Code/Intergrate/Test Login page | QuocTHHE150051 |  | Done
Iter1 | Vertical Prototype | Code/Intergrate/Test Register page | QuocTHHE150051 |  | Done
Iter1 | Design Overview | Login and Register | QuocTHHE150051 |  | Done
Iter2 | Vertical Prototype | Code EditProfile | Anhdnhhe150204 |  | Done
Iter2 | Data | Find and Add data to Database | Anhdnhhe150204 |  | Done
Iter2 | Vertical Prototype | Code ManageCustomers | HaGTHE153279 |  | Done
Iter2 | Vertical Prototype | Code ManageOrders | HaGTHE153279 |  | Done
Iter2 | Vertical Prototype | Code ManageRecipes | HaGTHE153279 |  | Doing
Iter2 | Vertical Prototype | Error paging | Minhtahe153458 |  | Done
Iter2 | Vertical Prototype | Java Script for Search, Filter, Pagination | NghiaHTHE153608 |  | Done
Iter2 | Vertical Prototype | Code View Recipe | NghiaHTHE153608 |  | Done
Iter2 | Vertical Prototype | Code View Ingredient | NghiaHTHE153608 |  | Done
Iter2 | Vertical Prototype | Code ForgetPassWord | QuocTHHE150051 |  | Done
Iter3 | Vertical Prototype | ChangePassWord | Anhdnhhe150204 |  | Doing
Iter3 | Vertical Prototype | Code ManageIngerdient | HaGTHE153279 |  | Doing
Iter3 | Vertical Prototype | Code ManageCategory | HaGTHE153279 |  | Done
Iter3 | Vertical Prototype | View Share | Minhtahe153458 |  | Doing
Iter3 | Vertical Prototype | Code View Recipe Detail | NghiaHTHE153608 |  | Done
Iter3 | Vertical Prototype | Code Ingredient Detail | NghiaHTHE153608 |  | Done
Iter3 | Vertical Prototype | Code View Homepage | NghiaHTHE153608 |  | Done
Iter3 | Vertical Prototype | Post Recipes | QuocTHHE150051 |  | Doing
Iter3 | Vertical Prototype | View Liked recipes | QuocTHHE150051 |  | Doing
Iter4 | Vertical Prototype | Cart Detail | NghiaHTHE153608 |  | Done
Iter4 | Vertical Prototype | Button "Add to Cart" | NghiaHTHE153608 |  | Done
Iter4 | Vertical Prototype | Button "Buy Now" | NghiaHTHE153608 |  | Done
Iter4 | Vertical Prototype | Order Detail for Admin | HaGTHE153279 |  | Doing
Iter4 | Vertical Prototype | Recipe_Ingredien Link | HaGTHE153279 |  | Doing
Iter4 | Vertical Prototype | Contact page | Anhdnhhe150204 |  | Doing
Iter4 | Vertical Prototype | Favourite list | QuocTHHE150051 |  | Doing
Iter4 | Vertical Prototype | User order hIstory | QuocTHHE150051 |  | Doing
Iter4 | Vertical Prototype | Recipes Comment | Minhtahe153458 |  | Doing